## Project Scope and Budget
Scope of Work and Budget
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of Escondido
Project Type: |  | Capital | Note: for Planning and Climate Action Plan Projects, use the Planning and Climate Action Plan Project Template
Project Title: |  | Grand Avenue Vision Project
Part I: Project Overview
Project Location: |  | Grand Avenue between Maple St and Escondido Blvd, Escondido, CA 92025
Brief Project Summary: |  | The project will improve a downtown corridor with wider sidewalks, improved pedestrian crossings, and a roundabout in the City of Escondido.
Project Objectives: |  | This project will make Escondido's historic downtown area a safer and more attractive place for the community and businesses. The Project will install a roundabout at Grand and Maple, widen sidewalks along Grand Ave, upgrade lighting across the block, and install green stormwater elements and stormwater drains. These improvements will work together to support efforts to revitalize the area for ecomonic development and community utilization.
Part II: Scope of Work and Budget
[List the Project subtasks under each of the grey-shaded tasks below. Add the Deliverables for each grey-shaded task that corresponds to the subtasks listed below it. Include the SGIP Grant Amount and Matching Funds Amount total for each grey-shaded task by adding the total of all subtasks listed below. Add rows as needed. The Total Project Cost column will auto-calculate and is the sum of the SGIP grant and the matching funds. For subtask 3D, SANDAG will contract with a consultant to provide the baseline data collection and the grantee will not have any incurred cost other than minimal staff time to support the data collection effort (less than 8 hours).]
Task No. | Task Description |  |  | Task Outcome/Output |  | Deliverables |  | SGIP Grant Amount | Matching Funds Amount | Total Project Cost
1 | Project Planning and Development |  |  | Development of a neighborhood-level plan, corridor study, or community active transportation strategy and subsequent planning documents to support the project. |  | [List all deliverables applicable to the project. Examples: Planning document that serves as the foundation for future project development. Project planning document including purpose and need, conceptual engineering, and project alternatives. Evidence of stakeholder engagement during project development (community meetings, feedback received)] |  | 0 | 0 | 0
1A | [Enter subtask description.] |  |  | [Enter the desired outcome of the subtask. This is the objective that the subtask seeks to accomplish.] |  | [Enter deliverables associated with the subtask. Items must be quantified. Please be aware that if the project is selected for funding, the Grantee will be responsible for ensuring all deliverables listed here are provided.] |  | [Enter amount requested] | [Enter match (non-SGIP funds)] | 0
1B | [9 empty] | 0
1C | [9 empty] | 0
2 | Final Design and Environmental Clearance |  |  | Final design plans and environmental clearance under the California Environmental Quality Act, or evidence that environmental clearance is not required |  | [List all deliverables applicable to the project. Examples: Final project plans CEQA clearance document or agency-approved CEQA exemption] |  | 175000 | 275000 | 450000
2A | Engineering Design |  |  | Final Design of project |  | Final Project Plans |  | 125000 | 175000 | 300000
I | Environmental Clearance - COMPLETE |  |  |  |  | CEQA Clearance Document |  | 0 | 0 | 0
2C | Project Management |  |  | Staff Support of Design |  | Progress Reports |  | 50000 | 100000 | 150000
3 | Right-Of-Way Acquisition and All Necessary Entitlements |  |  | All right-of-way and necessary entitlements are secured |  | [List all deliverables applicable to the project. Examples: Right-of-entry permit from other public agencies, signed easement agreement with utility, utility relocations, project agreements with partners/stakeholders.] |  | 0 | 0 | 0
3A | All ROW/Entitlements COMPLETE | [6 empty] | 0 | 0 | 0
3B | [9 empty] | 0
3C | [9 empty] | 0
3D | Baseline Data Collection |  |  | Baseline data on the project area is collected to be able to compare to post-construction data to demonstrate how the improvements have been utilized. |  | Baseline data collection plan is developed by a SANDAG consultant with input and assistance from the grantee |  | 0 | 0 | 0
4 | Construction Contracting |  |  | Construction bid documents are developed and put out to bid, the construction contractor is identified, and the contract is executed, public groundbreaking ceremony |  | [List all deliverables applicable to the project. Examples: Issued construction IFB with plans, issued addenda, advertisement of IFB, pre-bid sign-in sheet, bid tabulation summary, approval of construction contract, final signed contract with the construction contractor, conformed IFB and plans, photos and social media posts of groundbreaking ceremony.] |  | 15000 | 45000 | 60000
4A | RFP Released |  |  | Notify potential contractors |  | Request for Proposals |  | 5000 | 15000 | 20000
4B | Contractor Identified |  |  | Select Construction Contractor |  | Council Approval of Contract |  | 5000 | 15000 | 20000
4C | Contract Finalized |  |  | Finalize Contract |  | Finalized Contract |  | 5000 | 15000 | 20000
5 | Construction |  |  | Construction of the project occurs |  | [List all deliverables applicable to the project. The deliverables must be detailed and include the major line items that will be listed in the construction bid/contract. Examples: X linear feet of sidewalks, X directional signs, X cubic yards of mulch, X street trees, etc.] |  | 1800000 | 1900000 | 3700000
5A | Construction |  |  |  |  | Roundabout at Maple and X |  | 1650000 | 1500000 | 3150000
5B | Construction Management, testing, inspection | [6 empty] | 0 | 200000 | 200000
5C | Tribal Monitoring | [6 empty] | 0 | 50000 | 50000
5D | Contingency (10%) | [6 empty] | 150000 | 150000 | 300000
6 | Project Closeout |  |  | Construction contractor is relieved of maintenance, city council or other approval is attained, project is open to the public |  | [List all deliverables applicable to the project. Examples: City Council agenda accepting the construction project, relief of maintenance letter to the construction contractor, photos of ribbon cutting ceremony with the public.] |  | 10000 | 30000 | 40000
6A | Contract Closeout |  |  |  |  | Notice of Completion |  | 10000 | 30000 | 40000
6B | [9 empty] | 0
6C | [9 empty] | 0
TOTAL PROJECT COST: | [7 empty] | 2000000 | 2250000 | 4250000
Part III: Summary of Funding
[This information will be populated using information from Part II. Make a selection in the unshaded cell only.]
Total Project Cost: |  | 4250000
Total Grant Request: |  | 2000000
Total Matching Funds: |  | 2250000
Grant Percentage: |  |  | 47.06%
Matching Funds Percentage: |  |  | 52.94%
Will any of the matching funds be from the TransNet Local Street and Road program? |  |  | Yes
Part IV: Project Budget and Expenditures Per Fiscal Year
[SANDAG staff will use this information for the Regional Transportation Improvement Program (RTIP) if this project receives funding. Fill in the unshaded cells only.]
Category* | Fiscal Year (FY) 2026 (NTP - June 30, 2026) |  | Fiscal Year (FY) 2027 (July 1, 2026 - June 30, 2027) |  | Fiscal Year (FY) 2028 (July 1, 2027 - June 30, 2028) |  | Fiscal Year (FY) 2029 (July 1, 2028 - June 30, 2029) |  | Total Grant Amount | Total Matching Funds | Total Project Cost
| Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
PE | 125000 | 225000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 175000 | 275000 | 450000
RW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | 0 | 0 | 1800000 | 1900000 | 25000 | 75000 | 0 | 0 | 1825000 | 1975000 | 3800000
Total | 125000 | 225000 | 1850000 | 1950000 | 25000 | 75000 | 0 | 0 | 2000000 | 2250000 | 4250000
*Key
Category | Category Description
PE | Planning, Environmental, and Engineering
RW | Right-of-Way
CON | Construction
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New field in response to TPA.

## Project Schedule
Project Schedule
Applicant Name: |  | City of Escondido |  |  |  |  | Smart Growth Incentive Program - Climate Action Plan
Smart Growth Incentive Program - Complete Streets Policy
Project Type: |  | Capital | Note: for Planning and Climate Action Plan Projects, use the Planning and Climate Action Plan Project Template
Project Title: |  | Grand Avenue Vision Project |  |  |  |  | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital
Part II: Project Schedule
Task No. | Task Description |  |  | Start Date | Completion Date | Duration
1 | Project Planning and Development
1A | COMPLETE |  |  | 0 | 0 | 0
1B
1C
2 | Final Design and Environmental Review
2A | Engineering Design |  |  | 3 | 15 | 12
2B | Environmental Clearance - COMPLETE |  |  | 0 | 0 | 0
2C | Project Management |  |  | 3 | 15 | 12
3 | Right-Of-Way Acquisition and All Necessary Entitlements
3A | All ROW/Entitlements COMPLETE |  |  | 0 | 0 | 0
3B
3C
3D | Baseline Data Collection |  |  | [This can be left blank. SANDAG will fill this in with input from the Grantee once the schedule is finalized.] | [This can be left blank. SANDAG will fill this in with input from the Grantee once the schedule is finalized.] | [This can be left blank. SANDAG will fill this in with input from the Grantee once the schedule is finalized.]
4 | Construction Contracting
4A | RFP Released |  |  | 16 | 17 | 1
4B | Contractor Identified |  |  | 17 | 17 | 0
4C | Contract Finalized |  |  | 17 | 18 | 1
5 | Construction
5A | Construction/Contingency |  |  | 18 | 22 | 4
5B | Construction Management, testing, inspection |  |  | 18 | 22 | 4
5C | Tribal Monitoring |  |  | 18 | 22 | 4
6 | Project Closeout |  |  |  | [Per SANDAG Board Policy No. 035, enter the date when the construction contractor will be relieved of its maintenance responsibilities.]
6A | Contract Closeout |  |  | 22 | 24 | 2
6B
6C
Total Project Duration (In Months from NTP): | [5 empty] | 24

## SSB - with ICR (hidden)
Scope, Schedule, and Budget Worksheet
Grant Program: | [10 empty] | Smart Growth Incentive Program - Capital Project
Will the matching funds include TransNet Local Streets and Road (LSI)? | [10 empty] | Smart Growth Incentive Program - Planning Project
Jurisdiction: | [10 empty] | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital Project
Part I: Project Overview | [10 empty] | Smart Growth Incentive Program - Complete Streets Policy
Project Title: |  | [Copy and paste from application] | [8 empty] | Smart Grwoth Incentive Program - Climate Action Plan
Project Limit: |  | [Copy and paste from application]
Yes
Project Summary: |  | [Copy and paste from application] | [8 empty] | No
Part II: Scope of Work, Schedule, and Budget
Propose tasks, deliverables, a timeframe, and a budget for implementing the project. The project schedule must be based on "Months from Notice to Proceed" (NTP) and should comply with Board Policy No. 035 timelines. The Total Project Cost column will auto-calculate. Capital projects are required to include $5,000 for baseline bike and pedestrian data collection. If this SSB is for a SGIP Planning, ATGP Non-Capital, SGIP - CAP, or SGIP - Complete Streets Policy project, overwrite line item 1 in the table below.
Task No. | Task Description |  |  | Deliverables |  | Start Date | Completion Date | Total Project Cost |  | Indirect Cost
Enter Task or Subtask Number (tailor as needed) | Enter task descriptions. Please limit tasks to 3 - 6 main tasks. Limit sub-tasks to major milestones. |  |  | Enter deliverables associated with each task. |  | Enter start date as number of months from NTP. Enter whole numbers only. | Enter end date as number of months from NTP. Enter whole numbers only. | Enter cost to complete each task. Sub-tasks should not have an associated cost. The total cost of all tasks should equal the total project cost (grant funds requested + matching funds). |  | If applicable, enter the approved indirect cost rate percentage in the box below
15%
1 | Collect Baseline Data (required for Capital projects only; remove this task if it is a planning project) |  |  | Baseline Data Collection Plan; Raw Bike/Ped Data |  |  |  | 5000 |  | 5750
2 | [7 empty] | 0 |  | 0
2a | [7 empty] | 0 |  | 0
2b | [7 empty] | 0 |  | 0
3 | [7 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
TOTAL PROJECT COST (grant request funds + matching funds): | [8 empty] | 5000 | 5750
Seasonal Constraints
As applicable, identify any seasonal constraints that may require the overall project, or specific tasks, to begin or be completed by a specific date:
Part III: Summary of Funding
| Total project cost: |  |  |  |  | 5000
| Total grant amount requested from SANDAG: |  |  |  |  | [Insert grant amount requested]
| Total match amount that will be contributed: |  |  |  |  | [Insert match contribution]
| SANDAG grant % contribution: |  |  |  |  | #VALUE!
| Match % contribution: |  |  |  |  | #VALUE!
Will the matching funds include TransNet Local Streets and Road (LSI)?
Part IV: Project Budget Expenditures per Year
SANDAG staff will reference this information for RTIP programming if this project receives funding.
Category* |  | Fiscal Year (FY) 2019 (July 1, 2018 - June 30, 2019) |  | FY 2020 (if applicable) (July 1, 2019 - June 30, 2020) |  | FY 2021 (if applicable) (July 1, 2020 - June 30, 2021) |  | FY 2022 (if applicable) (July 1, 2021 - June 30, 2022)
|  | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
ENV/ENGR
ROW
CONSTRUCTION
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Category* |  | FY 2023 (if applicable) (July 1, 2022 - June 30, 2023) |  | Total Grant Amount | Total Matching Funds | Total Project Cost |  | *Key
|  | Grant Amount | Match Amount |  |  |  |  | Category | Category Description
ENV/ENGR |  |  |  | 0 | 0 | 0 |  | ENV/ENGR | Environmental, Engineering, and Planning
ROW |  |  |  | 0 | 0 | 0
CONSTRUCTION |  |  |  | 0 | 0 | 0 |  | ROW | Right-of-Way
Total |  | 0 | 0 | 0 | 0 | 0 |  | CONSTRUCTION | Construction