## Project Scope and Budget
Scope of Work and Budget
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of Vista
Project Type: |  | Climate Action Plan |  | [Select from the options in the dropdown field. Note: for Capital Projects, use the Capital Project Template.]
Project Title: |  | Updating the City of Vista's Climate Action Plan
Part I: Project Overview
Project Location: |  | City of Vista
Brief Project Summary: |  | The City of Vista will be updating their 2021 Climate Action Plan.
Project Objectives: |  | 1. Adopt Climate Action Plan Update for the City of Vista
Part II: Scope of Work and Budget
[List the main project tasks in the grey-shaded spaces below. Include the task description, task outcome/output, deliverables, and grant and matching funds amount. Under each project task, include the subtasks that will be necessary to complete the main project task and include the subtask outcome/output, deliverables, and grant and matching funds. Add rows as needed. The Total Project Cost column will auto-calculate and is the sum of the SGIP grant and the matching funds.]
Task No. | Task Description |  |  | Task Outcome/Output |  | Deliverables |  | SGIP Grant Amount | Matching Funds Amount | Total Project Cost
1 | Project Management |  |  | Oversee project workflow |  | Project schedule, resource allocation plan |  | 0 | 45000 | 45000
1A | Kick off meeting and project initiation |  |  | Establish project objectives and team roles |  | Meeting agenda, minutes, project charter |  | 5000 | 0 | 5000
1B | Ongoing project management |  |  | Monitor project progress |  | status reports, updated project timeline |  | 20000 |  | 20000
2 | Community Engagement |  |  | Foster community involvement |  | Engagement strategy document, participant feedback |  | 55000 | 40000 | 95000
2A | Community Engagement Plan |  |  | Develop structured approach for stakeholder involvement |  | Final community engagement plan |  | 5000 | 0 | 5000
2B | Internal Working Group Meetings (4) |  |  | Facilitate internal communication and collaboration |  | Meeting agendas, summaries, action items |  | 10000 | 0 | 10000
2C | Community Workshops (2) and interpretation services |  |  | Gather public input and provide accessibility |  | Workshop materials, photos, feedback summary |  | 20000 | 0 | 20000
2D | Focus Groups with CBO's (2) |  |  | Gather targeted insights from community leaders |  | Focus group findings, recommendations report |  | 5000 | 0 | 5000
2E | Online engagement and project website |  |  | Enhance digital communication and outreach |  | Live project website, online engagement analytics |  | 25000 | 0 | 25000
2F | Community Engagement summary |  |  | Compile community feedback and insights |  | Comprehensive engagement summary report |  | 10000 | 0 | 10000
2G | City Council Study Sessions (4) |  |  | Present project updates and seek council feedback |  | Presentation materials, meeting notes |  | 10000 | 0 | 10000
3 | Climate Action and Adaptation |  |  | Develop climate strategies |  | Strategy report, stakeholder input documents |  | 125000 | 0 | 125000
3A | Vulnerability Assessment |  |  | Identify climate vulnerabilities in the community |  | Vulnerability assessment report |  | 35000 | 0 | 35000
3B | GHG Inventory |  |  | Quantify greenhouse gas emissions |  | GHG inventory report |  | 35000 | 0 | 35000
3C | GHG Forecasts and Reduction Targets |  |  | Establish future emission scenarios |  | GHG forecast report, reduction target recommendations |  | 27500 | 0 | 27500
3D | Climate Action and Adaptation Strategies |  |  | Formulate actionable strategies |  | Strategy document |  | 27500 | 0 | 27500
4 | Implementation and Monitoring |  |  | Design implementation framework |  | Implementation plan, monitoring strategy |  | 75000 | 0 | 75000
4A | Implementation Cost Analysis |  |  | Evaluate financial implications |  | Cost analysis report |  | 25000 | 0 | 25000
4B | Cost/Benefit Analysis |  |  | Assess overall project value |  | Cost/benefit analysis report |  | 25000 | 0 | 25000
4C | Implentation and Monitoring |  |  | Develop implementation and monitoring plan |  | completed plan |  | 25000 | 0 | 25000
5 | Climate Action Plan Document Update |  |  | Revise and update CAP |  | Adopted Climate Action Plan |  | 60000 | 0 | 60000
5A | CAP Outline |  |  | Structure the Climate Action Plan |  | CAP outline document |  | 15000 | 0 | 15000
5B | Administrtive Drafts |  |  | Prepare preliminary drafts for review |  | Administrative draft documents |  | 15000 | 0 | 15000
5C | Public Review |  |  | Gather public feedback on CAP |  | Public review feedback summary |  | 15000 | 0 | 15000
5D | Final CAP |  |  | Complete Climate Action Plan Update for adoption |  | Final CAP document |  | 15000 | 0 | 15000
6 | Environmental Analysis |  |  | Examine potential environmental impacts |  | Environmental analysis report |  | 20000 | 0 | 20000
6A | Draft Addendum |  |  | Provide supplementary content |  | Draft addendum document |  | 10000 | 0 | 10000
6B | Final Addendum |  |  | Complete the supplementary content |  | Final addendum document |  | 10000 | 0 | 10000
TOTAL PROJECT COST: | [7 empty] | 335000 | 85000 | 420000
Part III: Summary of Funding
[This information will be populated using information from Part II. Make a selection in the unshaded cell only.]
Total Project Cost: |  | 420000
Total Grant Request: |  | 335000
Total Matching Funds: |  | 85000
Grant Percentage: |  |  | 79.76%
Matching Funds Percentage: |  |  | 20.24%
Will any of the matching funds be from the TransNet Local Street and Road program? |  |  | No
Part IV: Project Budget and Expenditures Per Fiscal Year
[SANDAG staff will use this information for the Regional Transportation Improvement Program (RTIP) if this project receives funding. Fill in the unshaded cells only.]
Category* | Fiscal Year (FY) 2026 (NTP - June 30, 2026) |  | Fiscal Year (FY) 2027 (July 1, 2026 - June 30, 2027) |  | Fiscal Year (FY) 2028 (July 1, 2027 - June 30, 2028) |  | Fiscal Year (FY) 2029 (July 1, 2028 - June 30, 2029) |  | Total Grant Amount | Total Matching Funds | Total Project Cost
| Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
PE | 93000 | 54000 | 125000 | 15500 | 117000 | 15500 |  | 0 | 335000 | 85000 | 420000
RW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 93000 | 54000 | 125000 | 15500 | 117000 | 15500 | 0 | 0 | 335000 | 85000 | 420000
*Key
Category | Category Description
PE | Planning, Environmental, and Engineering
RW | Right-of-Way
CON | Construction
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New field in response to TPA.

## Project Schedule
Project Schedule
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of Vista |  |  |  | Smart Growth Incentive Program - Climate Action Plan
Smart Growth Incentive Program - Complete Streets Policy
Project Type: |  | Climate Action Plan | [Select from the options in the dropdown field. Note: for Capital Projects, use the Capital Project Template.]
Project Title: |  | Updating the City of Vista's Climate Action Plan |  |  |  | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital
Part II: Project Schedule
[Propose a timeframe for each Project task and subtask. The schedule must use the same tasks and subtasks that are in the Scope of Work and be based on the number of months from the Notice to Proceed (NTP).]
Task No. | Task Description |  | Start Date | Completion Date | Duration
1 | Project Management |  | 2025-10-01 | 2028-03-01 | 30
1A | Kick off meeting and project initiation |  | 1 | 1 | 1
1B | Ongoing project management |  | 1 | 30 | 30
2 | Community Engagement |  | 2 | 24 | 23
2A | Community Engagement Plan |  | 2 | 2 | 1
2B | Internal Working Group Meetings (4) |  | 3 | 24 | 22
2C | Community Workshops (2) and interpretation services |  | 3 | 9 | 7
2D | Focus Groups with CBO's (2) |  | 3 | 9 | 7
2E | Online engagement and project website |  | 3 | 4 | 2
2F | Community Engagement summary |  | 10 | 11 | 2
2G | City Council Study Sessions (4) |  | 11 | 24 | 14
3 | Climate Action and Adaptation |  | 2 | 8 | 7
3A | Vulnerability Assessment |  | 2 | 8 | 7
3B | GHG Inventory |  | 2 | 8 | 7
3C | GHG Forecasts and Reduction Targets |  | 2 | 8 | 7
3D | Climate Action and Adaptation Strategies |  | 2 | 8 | 7
4 | Implementation and Monitoring |  | 9 | 13 | 5
4A | Implementation Cost Analysis |  | 9 | 13 | 5
4B | Cost/Benefit Analysis |  | 9 | 13 | 5
4C | Implentation and Monitoring plan |  | 9 | 13 | 5
5 | Climate Action Plan Document Update |  | 9 | 25 | 18
5A | CAP Outline |  | 9 | 9 | 1
5B | Administrtive Drafts |  | 9 | 17 | 9
5C | Public Review |  | 17 | 18 | 2
5D | Final CAP |  | 19 | 24 | 6
6 | Environmental Analysis |  | 25 | 30 | 6
6A | Draft Addendum |  | 25 | 26 | 2
6B | Final Addendum |  | 26 | 30 | 5
Total Project Duration (In Months from NTP): |  |  |  |  | 30

## SSB - with ICR (hidden)
Scope, Schedule, and Budget Worksheet
Grant Program: | [10 empty] | Smart Growth Incentive Program - Capital Project
Will the matching funds include TransNet Local Streets and Road (LSI)? | [10 empty] | Smart Growth Incentive Program - Planning Project
Jurisdiction: | [10 empty] | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital Project
Part I: Project Overview | [10 empty] | Smart Growth Incentive Program - Complete Streets Policy
Project Title: |  | [Copy and paste from application] | [8 empty] | Smart Grwoth Incentive Program - Climate Action Plan
Project Limit: |  | [Copy and paste from application]
Yes
Project Summary: |  | [Copy and paste from application] | [8 empty] | No
Part II: Scope of Work, Schedule, and Budget
Propose tasks, deliverables, a timeframe, and a budget for implementing the project. The project schedule must be based on "Months from Notice to Proceed" (NTP) and should comply with Board Policy No. 035 timelines. The Total Project Cost column will auto-calculate. Capital projects are required to include $5,000 for baseline bike and pedestrian data collection. If this SSB is for a SGIP Planning, ATGP Non-Capital, SGIP - CAP, or SGIP - Complete Streets Policy project, overwrite line item 1 in the table below.
Task No. | Task Description |  |  | Deliverables |  | Start Date | Completion Date | Total Project Cost |  | Indirect Cost
Enter Task or Subtask Number (tailor as needed) | Enter task descriptions. Please limit tasks to 3 - 6 main tasks. Limit sub-tasks to major milestones. |  |  | Enter deliverables associated with each task. |  | Enter start date as number of months from NTP. Enter whole numbers only. | Enter end date as number of months from NTP. Enter whole numbers only. | Enter cost to complete each task. Sub-tasks should not have an associated cost. The total cost of all tasks should equal the total project cost (grant funds requested + matching funds). |  | If applicable, enter the approved indirect cost rate percentage in the box below
15%
1 | Collect Baseline Data (required for Capital projects only; remove this task if it is a planning project) |  |  | Baseline Data Collection Plan; Raw Bike/Ped Data |  |  |  | 5000 |  | 5750
2 | [7 empty] | 0 |  | 0
2a | [7 empty] | 0 |  | 0
2b | [7 empty] | 0 |  | 0
3 | [7 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
TOTAL PROJECT COST (grant request funds + matching funds): | [8 empty] | 5000 | 5750
Seasonal Constraints
As applicable, identify any seasonal constraints that may require the overall project, or specific tasks, to begin or be completed by a specific date:
Part III: Summary of Funding
| Total project cost: |  |  |  |  | 5000
| Total grant amount requested from SANDAG: |  |  |  |  | [Insert grant amount requested]
| Total match amount that will be contributed: |  |  |  |  | [Insert match contribution]
| SANDAG grant % contribution: |  |  |  |  | #VALUE!
| Match % contribution: |  |  |  |  | #VALUE!
Will the matching funds include TransNet Local Streets and Road (LSI)?
Part IV: Project Budget Expenditures per Year
SANDAG staff will reference this information for RTIP programming if this project receives funding.
Category* |  | Fiscal Year (FY) 2019 (July 1, 2018 - June 30, 2019) |  | FY 2020 (if applicable) (July 1, 2019 - June 30, 2020) |  | FY 2021 (if applicable) (July 1, 2020 - June 30, 2021) |  | FY 2022 (if applicable) (July 1, 2021 - June 30, 2022)
|  | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
ENV/ENGR
ROW
CONSTRUCTION
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Category* |  | FY 2023 (if applicable) (July 1, 2022 - June 30, 2023) |  | Total Grant Amount | Total Matching Funds | Total Project Cost |  | *Key
|  | Grant Amount | Match Amount |  |  |  |  | Category | Category Description
ENV/ENGR |  |  |  | 0 | 0 | 0 |  | ENV/ENGR | Environmental, Engineering, and Planning
ROW |  |  |  | 0 | 0 | 0
CONSTRUCTION |  |  |  | 0 | 0 | 0 |  | ROW | Right-of-Way
Total |  | 0 | 0 | 0 | 0 | 0 |  | CONSTRUCTION | Construction