## Project Scope and Budget
Scope of Work and Budget
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of San Diego
Project Type: |  | Climate Action Plan |  | [Select from the options in the dropdown field. Note: for Capital Projects, use the Capital Project Template.]
Project Title: |  | City of San Diego Climate Action Plan Update
Part I: Project Overview
Project Location: |  | The city limits of the City of San Diego.
Brief Project Summary: |  | The project is an update of the City’s Climate Action Plan (CAP), which was adopted in 2022. The overarching purpose is to identify an updated package of actions the City can take to reduce greenhouse gas (GHG) emissions to levels in alignment with State goals in ways that achieve core benefits, including increased climate resilience, and equitable outcomes for local communities. An equitable outreach and engagement strategy will be prepared at the project outset so that opportunities for all community members to receive information and provide input are incorporated into the entirety of the CAP Update development process. An updated baseline emissions inventory, future projections, and reduction targets will be prepared to ensure the CAP Update is informed by the most recent and best available data, methodology, and best practices. New and revised measures and actions will be developed and quantified to substantiate how the City will reduce projected emissions to levels that meet or exceed its targets. Measures and actions will also be analyzed to identify potential for increased climate resilience, community benefits, and equitable outcomes as well as costs, economic impact, and feasible funding and financing mechanisms. The CAP Update will also address implementation of the updated measures and actions, set forth mechanisms for monitoring and amending the plan, and identify timing of future CAP Updates.
Project Objectives: |  | The City has the following project objectives for the CAP Update:
Provide opportunities for all community members to be informed and participate in the development of updated measures and actions
Prepare an updated baseline emissions inventory, future projections, and reduction targets using the most recent and best available data, methodology, and best practices
Develop a set of new and revised measures and actions to meet or exceed the updated targets
Complete analysis of measures and actions to inform implementation and prioritization, including cost, economic impact, funding options, and potential for increased climate resilience, community benefits, equitable outcomes, and feasible implementation
Set forth implementation details for measures and actions including timing, implementation mechanism, and responsible City departments
Establish mechanisms for monitoring and amending the CAP Update and identify timing of future CAP Updates
Part II: Scope of Work and Budget
[List the main project tasks in the grey-shaded spaces below. Include the task description, task outcome/output, deliverables, and grant and matching funds amount. Under each project task, include the subtasks that will be necessary to complete the main project task and include the subtask outcome/output, deliverables, and grant and matching funds. Add rows as needed. The Total Project Cost column will auto-calculate and is the sum of the SGIP grant and the matching funds.] | [11 empty] | DO NOT DELETE (HIDE BEFORE SUBMITTAL)
[14 empty] | FY26 |  | FY27 |  | FY28 |  | TOTAL
Task No. | Task Description |  |  | Task Outcome/Output |  | Deliverables |  | SGIP Grant Amount | Matching Funds Amount | Total Project Cost |  |  |  | SGIP | Match | SGIP | Match | SGIP | March | SGIP | March | Combined
1 | Consultant Procurement: Release a Request for Proposals (or equivalent solicitation for competitive bids), evaluate bids, and select and onboard a consultant |  |  | Consultant selection and onboarding |  | Bid documents, Kick-off meeting agenda and notes |  | 2500 | 625.4375 | 3125.4375 |  | 10/1/25 - 1/31/26 | FY26 | 2500 | 625.4375 | 0 | 0 | 0 | 0 | 2500 | 625.4375 | 3125.4375
2 | Equitable Community Outreach and Engagement |  |  | See below for Tasks 2A and 2B |  | See below for Tasks 2A and 2B |  | 82500 | 20639.4375 | 103139.4375 |  | 2/1/26 - 6/30/27
2A | Equitable Community Outreach and Engagement Strategy |  |  | CAP Update-specific strategy for conducting outreach and engagement |  | Draft and Final Equitable Outreach and Engagement Strategy |  | 25000 | 6254.375 | 31254.375 |  | 2/1/26 - 4/30/26 | FY26 | 25000 | 6254.375 | 0 | 0 | 0 | 0 | 25000 | 6254.375 | 31254.375
2B | Outreach and Engagement Events, Surveys, Materials, and Communications |  |  | All community members have realistic opportunities to receive information and provide input in proportion to their circumstances and needs |  | At least one event per quarter, with interpretation services (as needed); Outreach materials, including translated materials (as needed); Written outreach summaries that include: community comments and input, event locations, number of attendees and demographics (one written summary per event/survey instrument; one written summary addressing all outreach and engagement events/surveys conducted during duration of CAP Update) |  | 57500 | 14385.0625 | 71885.0625 |  | 5/1/26 - 6/30/27 | FY26 (2 mos.); FY 27 (12 mos. | 9583.3333 | 2397.5104 | 47916.6667 | 11987.5521 | 0 | 0 | 57500 | 14385.0625 | 71885.0625
2D | [9 empty] | 0
3 | Greenhouse Gas (GHG) Emissions Inventory, Projections, Reduction Targets |  |  | An updated understanding of existing and projected future levels of GHG emissions from community-wide activities and sources; updated near- and long-term GHG reduction targets aligned with State goals and plans for achieving net zero emissions; gap between projected emissions levels and levels needed to achieve targets |  | Draft and Final technical report documenting data sources, methodologies, and references used to prepare the inventory, projections, and establish the reduction targets |  | 75000 | 18763.125 | 93763.125 |  | 2/1/26 - 6/30/26 | FY26 | 75000 | 18763.125 | 0 | 0 | 0 | 0 | 75000 | 18763.125 | 93763.125
3A | [9 empty] | 0
3B | [9 empty] | 0
3C | [9 empty] | 0
4 | GHG Reduction Measures and Implementing Actions |  |  | See below for Tasks 4A and 4B |  | See below for Tasks 4A and 4B |  | 190000 | 47533.25 | 237533.25 |  | 7/1/26 - 6/30/27
4A | GHG Reduction Emissions Potential, Core Community Benefits, Equitable Outcomes |  |  | An updated set of measures and actions including new and revised measure and action statements; new and revised performance targets; quantified GHG emissions reduction potential; and potential for increased climate resilience, core community benefits and equitable outcomes |  | Draft and Final technical workbook documenting data sources, methodologies, and references used to quantify GHG emissions reduction potential and evaluate increased climate resilience, core commuity benefits and equitable outcomes |  | 75000 | 18763.125 | 93763.125 |  | 7/1/26 - 12/31/26 | FY27 | 0 | 0 | 75000 | 18763.125 |  |  | 75000 | 18763.125 | 93763.125
4B | Cost, Economic, and Funding Analysis |  |  | An understanding of the following for the updated set of measures and actions: implementation costs (City government); participant costs (e.g., residents, tenants, businesses, property owners, developers); economic value impact; potential funding and financing mechanisms for implementation |  | Draft and Final technical report documenting data sources, methodologies, and references used in cost and funding analysis; Draft and Final Funding and Financing Strategy |  | 115000 | 28770.125 | 143770.125 |  | 1/1/27 - 6/30/27 | FY27 | 0 | 0 | 115000 | 28770.125 |  |  | 115000 | 28770.125 | 143770.125
4C | [9 empty] | 0
4D | [9 empty] | 0
4E | [9 empty] | 0
4F
5 | Draft and Final CAP Update Document |  |  | An accessible CAP Update document that clearly articulates and substantiates how the package of GHG reduction strategies, measures, and actions will feasibly achieve the City’s goals for GHG reduction, equity, and other core benefits; sets forth details for implementation; and establishes mechanisms for ongoing monitoring and reporting and timing of future CAP updates |  | Draft and Final CAP Update document, including summary of public comments; agendas and materials for public meetings and public hearings for CAP Update consideration and approval |  | 40000 | 10007 | 50007 |  | 4/1/27 - 12/31/27 | FY27 (3 mos); FY28 (6 mos.) | 0 | 0 | 10000 | 2501.75 | 30000 | 7505.25 | 40000 | 10007 | 50007
0
0
0
0
6 | CEQA Compliance |  |  | The City satisfies CEQA environmental review requirements for the CAP Update |  | CEQA compliance document (anticipated to be Addendum or other streamlined document tiering from previously certified environmental document) |  | 10000 | 2501.75 | 12501.75 |  |  | FY28 (6 mos.) | 0 | 0 | 0 | 0 | 10000 | 2501.75 | 10000 | 2501.75 | 12501.75
0
0
5C | [9 empty] | 0
TOTAL PROJECT COST: | [7 empty] | 400000 | 100070 | 500070 |  | 0.25017 |  | 112083.3333 | 28040.4479 | 247916.6667 | 62022.5521 | 40000 | 10007 | 400000 | 100070 | 500070
Part III: Summary of Funding
[This information will be populated using information from Part II. Make a selection in the unshaded cell only.]
Total Project Cost: |  | 500070
Total Grant Request: |  | 400000
Total Matching Funds: |  | 100070
Grant Percentage: |  |  | 79.99%
Matching Funds Percentage: |  |  | 20.01%
Will any of the matching funds be from the TransNet Local Street and Road program? |  |  | No
Part IV: Project Budget and Expenditures Per Fiscal Year
[SANDAG staff will use this information for the Regional Transportation Improvement Program (RTIP) if this project receives funding. Fill in the unshaded cells only.]
Category* | Fiscal Year (FY) 2026 (NTP - June 30, 2026) |  | Fiscal Year (FY) 2027 (July 1, 2026 - June 30, 2027) |  | Fiscal Year (FY) 2028 (July 1, 2027 - June 30, 2028) |  | Fiscal Year (FY) 2029 (July 1, 2028 - June 30, 2029) |  | Total Grant Amount | Total Matching Funds | Total Project Cost
| Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
PE | 112083.3333 | 28040.4479 | 247916.6667 | 62022.5521 | 40000 | 10007 | 0 | 0 | 400000 | 100070 | 500070
RW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 112083.3333 | 28040.4479 | 247916.6667 | 62022.5521 | 40000 | 10007 | 0 | 0 | 400000 | 100070 | 500070
*Key
Category | Category Description
PE | Planning, Environmental, and Engineering
RW | Right-of-Way
CON | Construction
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New field in response to TPA.

## Project Schedule
Project Schedule
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of San Diego | [6 empty] | Smart Growth Incentive Program - Climate Action Plan
Smart Growth Incentive Program - Complete Streets Policy
Project Type: |  | Climate Action Plan | [Select from the options in the dropdown field. Note: for Capital Projects, use the Capital Project Template.]
Project Title: |  | City of San Diego Climate Action Plan Update | [6 empty] | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital
Part II: Project Schedule
[Propose a timeframe for each Project task and subtask. The schedule must use the same tasks and subtasks that are in the Scope of Work and be based on the number of months from the Notice to Proceed (NTP).]
Task No. | Task Description |  | Start Date | Completion Date | Duration | Andrew's notes - hide or delete cells before submitting
1 | Consultant Procurement: Release a Request for Proposals (or equivalent solicitation for competitive bids), evaluate bids, and select and onboard a consultant |  | NTP | NTP + 4 months | 4 months | 10/1/25 - 1/31/26 | FY26 | 120 days for RFP per P&C guidance doc
2 | Equitable Community Outreach and Engagement |  | NTP + 4 months | NTP + 21 months | 17 months | 2/1/26 - 6/30/27 | see below
2A | Equitable Community Outreach and Engagement Strategy |  | NTP + 4 months | NTP + 7 months | 3 months | 2/1/26 - 4/30/26 | FY26
2B | Outreach and Engagement Events, Surveys, Materials, and Communications |  | NTP + 7 months | NTP + 21 months | 14 months | 5/1/26 - 6/30/27 | FY26 (2 mos.); FY 27 (12 mos.
2D
3 | Greenhouse Gas (GHG) Emissions Inventory, Projections, Reduction Targets |  | NTP + 4 months | NTP + 9 months | 5 months | 2/1/26 - 6/30/26 | FY26
3A |  |  | NTP + month | NTP + months | months
3B |  |  | NTP + month | NTP + months | months
3C |  |  | NTP + month | NTP + months | months
4 | GHG Reduction Measures and Implementing Actions |  | NTP + 9 months | NTP + 21 months | 12 months | 7/1/26 - 6/30/27 | see below
4A | GHG Reduction Emissions Potential, Core Community Benefits, Equitable Outcomes |  | NTP + 9 months | NTP + 15 months | 6 months | 7/1/26 - 12/31/26 | FY27
4B | Cost, Economic, and Funding Analysis |  | NTP + 15 months | NTP + 21 months | 6 months | 1/1/27 - 6/30/27 | FY27
4C
4D
4E
4F
5 | Draft and Final CAP Update Document |  | NTP + 18 months | NTP + 27 months | 9 months | 4/1/27 - 12/31/27 | FY27 (3 mos); FY28 (6 mos.)
6 | CEQA Compliance |  | NTP+ 21 months | NTP + 27 months | 9 months | 7/1/27 - 12/31/27 | FY28 (6 mos.)
5B
5C
27 months (total)

## SSB - with ICR (hidden)
Scope, Schedule, and Budget Worksheet
Grant Program: | [10 empty] | Smart Growth Incentive Program - Capital Project
Will the matching funds include TransNet Local Streets and Road (LSI)? | [10 empty] | Smart Growth Incentive Program - Planning Project
Jurisdiction: | [10 empty] | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital Project
Part I: Project Overview | [10 empty] | Smart Growth Incentive Program - Complete Streets Policy
Project Title: |  | [Copy and paste from application] | [8 empty] | Smart Grwoth Incentive Program - Climate Action Plan
Project Limit: |  | [Copy and paste from application]
Yes
Project Summary: |  | [Copy and paste from application] | [8 empty] | No
Part II: Scope of Work, Schedule, and Budget
Propose tasks, deliverables, a timeframe, and a budget for implementing the project. The project schedule must be based on "Months from Notice to Proceed" (NTP) and should comply with Board Policy No. 035 timelines. The Total Project Cost column will auto-calculate. Capital projects are required to include $5,000 for baseline bike and pedestrian data collection. If this SSB is for a SGIP Planning, ATGP Non-Capital, SGIP - CAP, or SGIP - Complete Streets Policy project, overwrite line item 1 in the table below.
Task No. | Task Description |  |  | Deliverables |  | Start Date | Completion Date | Total Project Cost |  | Indirect Cost
Enter Task or Subtask Number (tailor as needed) | Enter task descriptions. Please limit tasks to 3 - 6 main tasks. Limit sub-tasks to major milestones. |  |  | Enter deliverables associated with each task. |  | Enter start date as number of months from NTP. Enter whole numbers only. | Enter end date as number of months from NTP. Enter whole numbers only. | Enter cost to complete each task. Sub-tasks should not have an associated cost. The total cost of all tasks should equal the total project cost (grant funds requested + matching funds). |  | If applicable, enter the approved indirect cost rate percentage in the box below
15%
1 | Collect Baseline Data (required for Capital projects only; remove this task if it is a planning project) |  |  | Baseline Data Collection Plan; Raw Bike/Ped Data |  |  |  | 5000 |  | 5750
2 | [7 empty] | 0 |  | 0
2a | [7 empty] | 0 |  | 0
2b | [7 empty] | 0 |  | 0
3 | [7 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
TOTAL PROJECT COST (grant request funds + matching funds): | [8 empty] | 5000 | 5750
Seasonal Constraints
As applicable, identify any seasonal constraints that may require the overall project, or specific tasks, to begin or be completed by a specific date:
Part III: Summary of Funding
| Total project cost: |  |  |  |  | 5000
| Total grant amount requested from SANDAG: |  |  |  |  | [Insert grant amount requested]
| Total match amount that will be contributed: |  |  |  |  | [Insert match contribution]
| SANDAG grant % contribution: |  |  |  |  | #VALUE!
| Match % contribution: |  |  |  |  | #VALUE!
Will the matching funds include TransNet Local Streets and Road (LSI)?
Part IV: Project Budget Expenditures per Year
SANDAG staff will reference this information for RTIP programming if this project receives funding.
Category* |  | Fiscal Year (FY) 2019 (July 1, 2018 - June 30, 2019) |  | FY 2020 (if applicable) (July 1, 2019 - June 30, 2020) |  | FY 2021 (if applicable) (July 1, 2020 - June 30, 2021) |  | FY 2022 (if applicable) (July 1, 2021 - June 30, 2022)
|  | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
ENV/ENGR
ROW
CONSTRUCTION
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Category* |  | FY 2023 (if applicable) (July 1, 2022 - June 30, 2023) |  | Total Grant Amount | Total Matching Funds | Total Project Cost |  | *Key
|  | Grant Amount | Match Amount |  |  |  |  | Category | Category Description
ENV/ENGR |  |  |  | 0 | 0 | 0 |  | ENV/ENGR | Environmental, Engineering, and Planning
ROW |  |  |  | 0 | 0 | 0
CONSTRUCTION |  |  |  | 0 | 0 | 0 |  | ROW | Right-of-Way
Total |  | 0 | 0 | 0 | 0 | 0 |  | CONSTRUCTION | Construction