## Project Scope and Budget
Scope of Work and Budget
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of Imperial Beach
Project Type: |  | Climate Action Plan |  | [Select from the options in the dropdown field. Note: for Capital Projects, use the Capital Project Template.]
Project Title: |  | City of Imperial Beach Climate Action Plan Update
Part I: Project Overview
Project Location: |  | City-wide project. City of Imperial Beach jurisdictional boundaries.
Brief Project Summary: |  | To keep the City’s CAP current and effective, the city plans to update its Climate Action Plan, including the greenhouse gas emissions inventory, and develop new emission reduction strategies. This process will involve community outreach to gather input and ensure the plan meets local needs and priorities.
Project Objectives: |  | The purpose of this project is to update the City's Climate Action Plan to ensure the plan is robust and actionable, and effecitvely guides the City toward meeting its climate goals. The project aims to 1. Establish a comprehensive and data-driven understanding of Imperial Beach's current and projected greenhouse gas (GHG) emissions. 2. Define clear and quantifiable GHG reduction targets for 2030 and 2045 that align with California's statewide climate goals. 3. Develop a concrete, measurable, and actionable strategy with specific and quantifiable GHG reduction measures. 4. Incorporate a framework for the ongoing monitoring and evaluation of the CAP's implementation and effectiveness.
Part II: Scope of Work and Budget
[List the main project tasks in the grey-shaded spaces below. Include the task description, task outcome/output, deliverables, and grant and matching funds amount. Under each project task, include the subtasks that will be necessary to complete the main project task and include the subtask outcome/output, deliverables, and grant and matching funds. Add rows as needed. The Total Project Cost column will auto-calculate and is the sum of the SGIP grant and the matching funds.]
Task No. | Task Description |  |  | Task Outcome/Output |  | Deliverables |  | SGIP Grant Amount | Matching Funds Amount | Total Project Cost
1 | GHG Emissions Forecasts & Reduction Measures | [6 empty] | 40000 |  | 40000
1A | GHG Reduction Measures |  |  | Identify comprehensive list of potential GHG reduction measures across relevant sectors. Quantify emission reductions for each measure. |  | Comprehensive list of quantified reductions measures |  | 20000 |  | 20000
1B | GHG Emission Forecasts |  |  | Develop "Business-as-Usual" (BAU) Greenhouse Gas (GHG) emissions forecasts for Imperial Beach, projecting future emissions without new local climate actions, but accounting for existing federal and state mandates. |  | Develop GHG Emission Reduction Targets for Imperial Beach using BAU GHG forecasts |  | 20000 |  | 40000
1C | [9 empty] | 0
2 | Community Engagement |  |  | Provide opportunities for community input. |  | Suggestions/proposals from community incorporated into plans. |  | 25000 |  | 25000
2A | [9 empty] | 0
2B | [9 empty] | 0
2C | [9 empty] | 0
3 | CAP Implementation, Monitoring, and Updates |  |  | Develop framework for ongoing monitoring of measure implementation. Tracking defined actions and regularly asessing actual GHG reductions achieved vs estimates. |  | Framework for ongoing monitoring of measure implementation and effectiveness and first CAP Update |  | 25000 |  | 25000
3A | [9 empty] | 0
3B | [9 empty] | 0
3C | [9 empty] | 0
4 | Smart Growth Training |  |  | Provide training to staff on smart growth |  | Increased number of staff trained on smart growth |  | 15000 |  | 15000
4A | [9 empty] | 0
4B | [9 empty] | 0
4C | [9 empty] | 0
5 | Updated Climate Action Plan & CAP Progress Report |  |  | Present CAP for Adoption to City Council |  | Adopted Climate Action Plan & Progress Report |  | 45000 |  | 45000
5A | [9 empty] | 0
5B | [9 empty] | 0
5C | [9 empty] | 0
TOTAL PROJECT COST: | [7 empty] | 150000 | 0 | 150000
Part III: Summary of Funding
[This information will be populated using information from Part II. Make a selection in the unshaded cell only.]
Total Project Cost: |  | 150000
Total Grant Request: |  | 150000
Total Matching Funds: |  | 0
Grant Percentage: |  |  | 100%
Matching Funds Percentage: |  |  | 0%
Will any of the matching funds be from the TransNet Local Street and Road program? |  |  | No
Part IV: Project Budget and Expenditures Per Fiscal Year
[SANDAG staff will use this information for the Regional Transportation Improvement Program (RTIP) if this project receives funding. Fill in the unshaded cells only.]
Category* | Fiscal Year (FY) 2026 (NTP - June 30, 2026) |  | Fiscal Year (FY) 2027 (July 1, 2026 - June 30, 2027) |  | Fiscal Year (FY) 2028 (July 1, 2027 - June 30, 2028) |  | Fiscal Year (FY) 2029 (July 1, 2028 - June 30, 2029) |  | Total Grant Amount | Total Matching Funds | Total Project Cost
| Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
PE | 150000 | [7 empty] | 150000 | 0 | 150000
RW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000
*Key
Category | Category Description
PE | Planning, Environmental, and Engineering
RW | Right-of-Way
CON | Construction
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New field in response to TPA.

## Project Schedule
Project Schedule
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of Imperial Beach |  |  |  | Smart Growth Incentive Program - Climate Action Plan
Smart Growth Incentive Program - Complete Streets Policy
Project Type: |  | Climate Action Plan | [Select from the options in the dropdown field. Note: for Capital Projects, use the Capital Project Template.]
Project Title: |  | City of Imperial Beach Climate Action Plan Update |  |  |  | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital
Part II: Project Schedule
[Propose a timeframe for each Project task and subtask. The schedule must use the same tasks and subtasks that are in the Scope of Work and be based on the number of months from the Notice to Proceed (NTP).]
Task No. | Task Description |  | Start Date | Completion Date | Duration
1 | GHG Emissions Forecasts & Reduction Measures |  | 0 | 6 | 6
1A | GHG Reduction Measures |  | 0 | 6 | 6
1B | GHG Emission Forecasts |  | 0 | 6 | 6
1C
2 | Community Engagement |  | 6 | 9 | 3
2A
2B
2C
3 | CAP Implementation, Monitoring, and Updates |  | 6 | 10 | 4
3A
3B
3C
4 | Smart Growth Training |  | 18 | 20 | 2
4A
4B
4C
5 | Updated Climate Action Plan |  | 10 | 14 | 4
5A | Progress Report |  | 24 | 36 | 12
5B
5C
Total Project Duration (In Months from NTP): |  |  |  |  | 36

## SSB - with ICR (hidden)
Scope, Schedule, and Budget Worksheet
Grant Program: | [10 empty] | Smart Growth Incentive Program - Capital Project
Will the matching funds include TransNet Local Streets and Road (LSI)? | [10 empty] | Smart Growth Incentive Program - Planning Project
Jurisdiction: | [10 empty] | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital Project
Part I: Project Overview | [10 empty] | Smart Growth Incentive Program - Complete Streets Policy
Project Title: |  | [Copy and paste from application] | [8 empty] | Smart Grwoth Incentive Program - Climate Action Plan
Project Limit: |  | [Copy and paste from application]
Yes
Project Summary: |  | [Copy and paste from application] | [8 empty] | No
Part II: Scope of Work, Schedule, and Budget
Propose tasks, deliverables, a timeframe, and a budget for implementing the project. The project schedule must be based on "Months from Notice to Proceed" (NTP) and should comply with Board Policy No. 035 timelines. The Total Project Cost column will auto-calculate. Capital projects are required to include $5,000 for baseline bike and pedestrian data collection. If this SSB is for a SGIP Planning, ATGP Non-Capital, SGIP - CAP, or SGIP - Complete Streets Policy project, overwrite line item 1 in the table below.
Task No. | Task Description |  |  | Deliverables |  | Start Date | Completion Date | Total Project Cost |  | Indirect Cost
Enter Task or Subtask Number (tailor as needed) | Enter task descriptions. Please limit tasks to 3 - 6 main tasks. Limit sub-tasks to major milestones. |  |  | Enter deliverables associated with each task. |  | Enter start date as number of months from NTP. Enter whole numbers only. | Enter end date as number of months from NTP. Enter whole numbers only. | Enter cost to complete each task. Sub-tasks should not have an associated cost. The total cost of all tasks should equal the total project cost (grant funds requested + matching funds). |  | If applicable, enter the approved indirect cost rate percentage in the box below
15%
1 | Collect Baseline Data (required for Capital projects only; remove this task if it is a planning project) |  |  | Baseline Data Collection Plan; Raw Bike/Ped Data |  |  |  | 5000 |  | 5750
2 | [7 empty] | 0 |  | 0
2a | [7 empty] | 0 |  | 0
2b | [7 empty] | 0 |  | 0
3 | [7 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
TOTAL PROJECT COST (grant request funds + matching funds): | [8 empty] | 5000 | 5750
Seasonal Constraints
As applicable, identify any seasonal constraints that may require the overall project, or specific tasks, to begin or be completed by a specific date:
Part III: Summary of Funding
| Total project cost: |  |  |  |  | 5000
| Total grant amount requested from SANDAG: |  |  |  |  | [Insert grant amount requested]
| Total match amount that will be contributed: |  |  |  |  | [Insert match contribution]
| SANDAG grant % contribution: |  |  |  |  | #VALUE!
| Match % contribution: |  |  |  |  | #VALUE!
Will the matching funds include TransNet Local Streets and Road (LSI)?
Part IV: Project Budget Expenditures per Year
SANDAG staff will reference this information for RTIP programming if this project receives funding.
Category* |  | Fiscal Year (FY) 2019 (July 1, 2018 - June 30, 2019) |  | FY 2020 (if applicable) (July 1, 2019 - June 30, 2020) |  | FY 2021 (if applicable) (July 1, 2020 - June 30, 2021) |  | FY 2022 (if applicable) (July 1, 2021 - June 30, 2022)
|  | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
ENV/ENGR
ROW
CONSTRUCTION
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Category* |  | FY 2023 (if applicable) (July 1, 2022 - June 30, 2023) |  | Total Grant Amount | Total Matching Funds | Total Project Cost |  | *Key
|  | Grant Amount | Match Amount |  |  |  |  | Category | Category Description
ENV/ENGR |  |  |  | 0 | 0 | 0 |  | ENV/ENGR | Environmental, Engineering, and Planning
ROW |  |  |  | 0 | 0 | 0
CONSTRUCTION |  |  |  | 0 | 0 | 0 |  | ROW | Right-of-Way
Total |  | 0 | 0 | 0 | 0 | 0 |  | CONSTRUCTION | Construction