## Project Scope and Budget
Scope of Work and Budget
Applicant Name: |  | City of National City
Project Type: |  | Climate Action Plan
Project Title: |  | National City Climate Action Plan Implementation Monitoring
Part I: Project Overview
Project Location: |  | City of National City, CA 91950
Brief Project Summary: |  | Implementation of an on-going monitoring program of CAP implementation, including regular tracking, and occasional re-inventory of greenhouse gas (GHG) emissions.
Project Objectives: |  | This project is intended to complete the implementation and monitoring components of the City's 2024 CAP. The implementation plan (under development) will need to be refined into departmental work plans and a monitoring framework developed to allow the City to track progress toward GHG emissions reductions targets as establlished through the FGPU and CAP adopted last year.
Part II: Scope of Work and Budget
Task No. | Task Description |  |  | Task Outcome/Output |  | Deliverables |  | SGIP Grant Amount | Matching Funds Amount | Total Project Cost
1 | Monitoring Framework |  |  | Three-year plan for iterative monitoring, reporting, public engagement and interdepartmental coordination |  | Framework and Collaboration tool |  | 27000 | 8000 | 35000
1A | Plan for 3-year monitoring and Re-intentory Cycles |  |  | The City to establish a 3-year framework for on-going implementation, monitoring and reporting for the 2024 CAP |  | A Framework Plan that can be replicated every three years |  | 15000 | 3000 | 18000
1B | Develop a interdepartmental collaboration tool |  |  | A spreadheet or tracking tool that can be shared among departments for track completion of CAP actions in the Implemenation Plan |  | Spreadsheet or tracking Tool |  | 12000 | 5000 | 17000
2 | Inventory Update (2024 Baseline) and BAU Forecast |  |  | Create updated inventory for 2024 |  |  |  | 72000 | 2000 | 74000
2A | Data Requests |  |  | Coordinate with service providers to obtain most recent base year data from internal and external sources (~2024) |  | Letters to service providers building on requests from adopted CAP inventory |  | 10000 | 2000 | 12000
2B | SANDAG 2025 ABM VMT modeling |  |  | Conduct CAP VMT modeling to account for land use and circulation changes that have occued since the 2018 model run using the new 2025 ABM model. |  | CAP VMT model Output for input into ClearPath |  | 35000 | 0 | 35000
2C | Update ClearPath Tool |  |  | Use the ClearPath tool to update the 2018 Inventory included in the 2024 CAP for a 2024 baseyear |  | Updated inventory |  | 27000 | 0 | 27000
3 | Public Engagement | [6 empty] | 54000 | 29000 | 83000
3A | Monitoring Dashboard - Web-based |  |  | A publicly access version of monitoring and reporting; web-based |  | Web-based reporting dashboard |  | 15000 | 7000 | 22000
3B | Engagement Plan |  |  | Idenitify specific engagment tasks/events to be completed over 3-year monitoring period |  | Engagement Plan |  | 15000 | 7000 | 22000
3C | Survey and/or Workshop - CAP Awareness/Satisifcation |  |  | Obtain stakeholder and public input on progress of CAP Implementation |  | Compiled survey results |  | 24000 | 15000 | 39000
4 | Departmental Work Plans and Checklist | [6 empty] | 39000 | 15000 | 54000
4A | Create up to 3 department workplans to facilitate CAP implementation |  |  | A detailed plan that allows implementing departments to demonstate how CAP actions are incorporated into work programs |  | Work Plans - up to 3 |  | 24000 | 10000 | 34000
4B | Create development CAP Checklist |  |  | A checklist that allows development projects to demonstrate consistency with the CAP and streamline CEQA review though 15183.5 CEQA Guidelines provisions |  | Development CAP Checklist |  | 15000 | 5000 | 20000
5 | Monitoring Report |  |  |  |  | Complete monitoring Report (2027) |  | 42500 | 5000 | 47500
5A | Compile Inventory data |  |  | Create a narrative and graphical presenation of updated inventory data and BAU forecast |  | Narrative and exhibits |  | 15000 |  | 15000
5B | Compilie community input |  |  | Present findings from community engagement in Task 3B |  | Narrative and exhibits |  | 12500 |  | 12500
5C | Complete Monitoring Report |  |  | Publish monitoring report before end of grant period (mid 2028) |  | Monitoring Report |  | 15000 | 5000 | 20000
TOTAL PROJECT COST: | [7 empty] | 234500 | 59000 | 293500
Part III: Summary of Funding
Total Project Cost: |  | 293500
Total Grant Request: |  | 234500
Total Matching Funds: |  | 59000
Grant Percentage: |  |  | 79.9%
Matching Funds Percentage: |  |  | 20.1%
Will any of the matching funds be from the TransNet Local Street and Road program?
Part IV: Project Budget and Expenditures Per Fiscal Year
Category* | Fiscal Year (FY) 2026 (NTP - June 30, 2026) |  | Fiscal Year (FY) 2027 (July 1, 2026 - June 30, 2027) |  | Fiscal Year (FY) 2028 (July 1, 2027 - June 30, 2028) |  | Fiscal Year (FY) 2029 (July 1, 2028 - June 30, 2029) |  | Total Grant Amount | Total Matching Funds | Total Project Cost
| Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
PE | 104000 | 42000 | 8000 | 5000 | 122500 | 12000 | 0 | 0 | 234500 | 59000 | 293500
RW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 104000 | 42000 | 8000 | 5000 | 122500 | 12000 | 0 | 0 | 234500 | 59000 | 293500
*Key
Category | Category Description
PE | Planning, Environmental, and Engineering
RW | Right-of-Way
CON | Construction
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New field in response to TPA.

## Project Schedule
Project Schedule
Applicant Name: |  | City of National City |  |  |  | Smart Growth Incentive Program - Climate Action Plan
Smart Growth Incentive Program - Complete Streets Policy
Project Type: |  | Climate Action Plan
Project Title: |  | City of National City, Community Development Department |  |  |  | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital
Part II: Project Schedule
Task No. | Task Description |  | Start Date | Completion Date | Duration
1 | Monitoring Framework |  | 0 | 4 | 4
1A | Plan for 3-year monitoring and re-intentory Cycles |  | 0 | 4 | 4
1B | Develop a interdepartmental collaboration tool |  | 2 | 4 | 2
1C
2 | Inventory Update (2024 Baseline) and BAU Forecast |  | 25 | 34 | 9
2A | Data Requests |  | 25 | 30 | 5
2B | SANDAG 2025 ABM VMT modeling |  | 25 | 30 | 5
2C | Update ClearPath Tool |  | 30 | 34 | 4
3 | Public Engagement |  | 0 | 36 | 36
3A | Monitoring Dashboard - Web-based |  | 3 | 6 | 3
3B | Engagement Plan |  | 0 | 3 | 3
3C | Survey and/or Workshop - CAP Awareness/Satisifcation |  | 3 | 36 | 33
4 | Departmental Work Plans and Checklist |  | 2 | 6 | 4
4A | Create up to 3 department workplans to facilitate CAP implementation |  | 2 | 6 | 4
4B | Create development CAP Checklist |  | 2 | 6 | 4
5 | Monitoring Report |  | 30 | 36 | 6
5A | Compile Inventory data |  | 30 | 34 | 4
5B | Compilie community input |  | 30 | 34 | 4
5C | Complete Monitoring Report |  | 34 | 36 | 2
Total Project Duration (In Months from NTP): |  |  |  |  | 36

## SSB - with ICR (hidden)
Scope, Schedule, and Budget Worksheet
Grant Program: | [10 empty] | Smart Growth Incentive Program - Capital Project
Will the matching funds include TransNet Local Streets and Road (LSI)? | [10 empty] | Smart Growth Incentive Program - Planning Project
Jurisdiction: | [10 empty] | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital Project
Part I: Project Overview | [10 empty] | Smart Growth Incentive Program - Complete Streets Policy
Project Title: |  | [Copy and paste from application] | [8 empty] | Smart Grwoth Incentive Program - Climate Action Plan
Project Limit: |  | [Copy and paste from application]
Yes
Project Summary: |  | [Copy and paste from application] | [8 empty] | No
Part II: Scope of Work, Schedule, and Budget
Propose tasks, deliverables, a timeframe, and a budget for implementing the project. The project schedule must be based on "Months from Notice to Proceed" (NTP) and should comply with Board Policy No. 035 timelines. The Total Project Cost column will auto-calculate. Capital projects are required to include $5,000 for baseline bike and pedestrian data collection. If this SSB is for a SGIP Planning, ATGP Non-Capital, SGIP - CAP, or SGIP - Complete Streets Policy project, overwrite line item 1 in the table below.
Task No. | Task Description |  |  | Deliverables |  | Start Date | Completion Date | Total Project Cost |  | Indirect Cost
Enter Task or Subtask Number (tailor as needed) | Enter task descriptions. Please limit tasks to 3 - 6 main tasks. Limit sub-tasks to major milestones. |  |  | Enter deliverables associated with each task. |  | Enter start date as number of months from NTP. Enter whole numbers only. | Enter end date as number of months from NTP. Enter whole numbers only. | Enter cost to complete each task. Sub-tasks should not have an associated cost. The total cost of all tasks should equal the total project cost (grant funds requested + matching funds). |  | If applicable, enter the approved indirect cost rate percentage in the box below
15%
1 | Collect Baseline Data (required for Capital projects only; remove this task if it is a planning project) |  |  | Baseline Data Collection Plan; Raw Bike/Ped Data |  |  |  | 5000 |  | 5750
2 | [7 empty] | 0 |  | 0
2a | [7 empty] | 0 |  | 0
2b | [7 empty] | 0 |  | 0
3 | [7 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
TOTAL PROJECT COST (grant request funds + matching funds): | [8 empty] | 5000 | 5750
Seasonal Constraints
As applicable, identify any seasonal constraints that may require the overall project, or specific tasks, to begin or be completed by a specific date:
Part III: Summary of Funding
| Total project cost: |  |  |  |  | 5000
| Total grant amount requested from SANDAG: |  |  |  |  | [Insert grant amount requested]
| Total match amount that will be contributed: |  |  |  |  | [Insert match contribution]
| SANDAG grant % contribution: |  |  |  |  | #VALUE!
| Match % contribution: |  |  |  |  | #VALUE!
Will the matching funds include TransNet Local Streets and Road (LSI)?
Part IV: Project Budget Expenditures per Year
SANDAG staff will reference this information for RTIP programming if this project receives funding.
Category* |  | Fiscal Year (FY) 2019 (July 1, 2018 - June 30, 2019) |  | FY 2020 (if applicable) (July 1, 2019 - June 30, 2020) |  | FY 2021 (if applicable) (July 1, 2020 - June 30, 2021) |  | FY 2022 (if applicable) (July 1, 2021 - June 30, 2022)
|  | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
ENV/ENGR
ROW
CONSTRUCTION
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Category* |  | FY 2023 (if applicable) (July 1, 2022 - June 30, 2023) |  | Total Grant Amount | Total Matching Funds | Total Project Cost |  | *Key
|  | Grant Amount | Match Amount |  |  |  |  | Category | Category Description
ENV/ENGR |  |  |  | 0 | 0 | 0 |  | ENV/ENGR | Environmental, Engineering, and Planning
ROW |  |  |  | 0 | 0 | 0
CONSTRUCTION |  |  |  | 0 | 0 | 0 |  | ROW | Right-of-Way
Total |  | 0 | 0 | 0 | 0 | 0 |  | CONSTRUCTION | Construction