## Project Scope and Budget
Scope of Work and Budget
Applicant Name: |  | City of San Marcos
Project Type: |  | Climate Action Plan
Project Title: |  | City of San Marcos Climate Action Plan Update
Part I: Project Overview
Project Location: |  | City of San Marcos, San Diego County, California
Brief Project Summary: |  | Update to existing City of San Marcos Climate Action Plan
Project Objectives: |  | 1. CAP Strategies # 2 and #3 and their respective measures will be revisited to align with SANDAG smart growth policy and future year regional ABM assumptions. 2. CAP strategies #1, #4 and #5, and their respective measures, will be revised to account for new and/or modified State mandates, legislation and/or code requirements. 3. Three authentic and creative public engagement events and actions such as “pop-up” demonstrations, walk audits, community bike/walk events, etc., and number of people engaged in them (disaggregated by demographics) 4. One to two suggestions/proposals from community engagement processes are incorporated into the CAP update. 5. Changes in carbon emissions (MTCO2e): Future year mitigated BAU forecast is demonstrated to meet City target set by CAP update.
Part II: Scope of Work and Budget
Task No. | Task Description |  |  | Task Outcome/Output |  | Deliverables |  | SGIP Grant Amount | Matching Funds Amount | Total Project Cost
1 | Climate Action Plan Update |  |  | Prepare a comprehensive administrative draft of the Climate Action Plan (CAP) Update and the Final Climate Action Plan Update document to be released for public review |  | Draft and Final CAP Update |  | 135000 | 4000 | 139000
1A | Inventory Update, Emissions Forecasts (BAU, Legislative BAU), Targets |  |  | Prepare a comprehensive Greenhouse Gas (GHG) Emissions Inventory update; Assess future transportation-based GHG emissions using SANDAG ABM and Vehicle Miles Traveled (VMT) data; Update the City's BAU Forecasts; Establish a GHG reduction target for the City |  | New GHG Emissions Inventory; Updated GHG emissions forecasts; Updated GHG Reduction Targets |  | 65000 | 0 | 65000
1B | Reduction Measures, Mitigated BAU Forecast and BCA |  |  | Update and/or develop new reduction measures to achieve targets; Complete future year mitigated forecast; Develop benefit costs-analysis spreadsheet |  | New or revised reduction strategies and measures; future year forecasts; Benefit-Cost Analysis Draft and Final |  | 40000 | 2000 | 42000
1C | Draft and Final Climate Action Plan |  |  | Prepare an administrative draft and final draft of a CAP Update |  | Administrative Draft and Final CAP Update |  | 30000 | 2000 | 32000
2 | Climate Action Plan Checklist |  |  | Update the CAP checklist to be applicable to the Climate Action Plan Update |  | Draft and Final CAP Checklist |  | 50000 | 2000 | 52000
3 | Negative Declaration |  |  | Prepare an administrative draft and final draft of an Initial Study (IS) / Negative Declaration (ND) to be submitted alongside the CAP Update for public review |  | Draft and Final ND |  | 80000 |  | 80000
3A | Administrative Draft Negative Declaration |  |  | Prepare administrative draft of Initial IS/ ND |  | Administrative Draft ND |  | 55000 |  | 55000
3B | Public Review Negative Declaration |  |  | Address City comments on administrative draft ND |  | Revised Draft ND |  | 10000 |  | 10000
3C | Final Negative Declaration |  |  | Prepare Final ND for adoption |  | Final ND |  | 15000 |  | 15000
4 | Community Outreach |  |  | Public engagement strategy development and implementation |  | Conduct public engagement |  | 50000 | 3450 | 53450
4A | Public Engagement Plan |  |  | Develop Draft and Final Public Engagement Plan in collaboration with the City's Communication and CAP teams. |  | Public Engagement Plan and Final Public Engagement Plan |  | 15000 |  | 15000
4B | Conduct public engagement |  |  | Implement Public Engagement Plan activities |  | Workshops, surveys or other means as described in the engagement plan |  | 35000 | 3450 | 38450
TOTAL PROJECT COST: | [7 empty] | 315000 | 9450 | 324450
Part III: Summary of Funding
Total Project Cost: |  | 324450
Total Grant Request: |  | 315000
Total Matching Funds: |  | 9450
Grant Percentage: |  |  | 97.09%
Matching Funds Percentage: |  |  | 2.913%
Will any of the matching funds be from the TransNet Local Street and Road program?
Part IV: Project Budget and Expenditures Per Fiscal Year
Category* | Fiscal Year (FY) 2026 (NTP - June 30, 2026) |  | Fiscal Year (FY) 2027 (July 1, 2026 - June 30, 2027) |  | Fiscal Year (FY) 2028 (July 1, 2027 - June 30, 2028) |  | Fiscal Year (FY) 2029 (July 1, 2028 - June 30, 2029) |  | Total Grant Amount | Total Matching Funds | Total Project Cost
| Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
PE | 67500 | 4000 | 140000 | 4000 | 107500 | 1450 |  |  | 315000 | 9450 | 324450
RW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 67500 | 4000 | 140000 | 4000 | 107500 | 1450 | 0 | 0 | 315000 | 9450 | 324450
*Key
Category | Category Description
PE | Planning, Environmental, and Engineering
RW | Right-of-Way
CON | Construction

## Project Schedule
Project Schedule
Applicant Name: |  | City of San Marcos |  |  |  | Smart Growth Incentive Program - Climate Action Plan
Smart Growth Incentive Program - Complete Streets Policy
Project Type: |  | Climate Action Plan
Project Title: |  | City of San Marcos Climate Action Plan Update |  |  |  | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital
Part II: Project Schedule
Task No. | Task Description |  | Start Date | Completion Date | Duration
1 | Climate Action Plan Update |  | 0 | 18 | 18
1A | Inventory Update, Emissions Forecasts (BAU, Legislative BAU), Targets |  | 0 | 6 | 6
1B | Reduction Measures, Mitigated BAU Forecast and BCA |  | 6 | 12 | 6
1C | Draft and Final CAP |  | 13 | 18 | 6
2 | Climate Action Plan Checklist |  | 13 | 18 | 6
3 | Negative Declaration |  | 19 | 30 | 12
3A | Administrative Draft Negative Declaration |  | 19 | 24 | 6
3B | Public Review ND |  | 25 | 27 | 3
3C | Final Negative Declaration |  | 28 | 30 | 3
4 | Community Outreach |  | 0 | 30 | 30
4A | Public Engagement Plan |  | 0 | 3 | 3
4B | Conduct public engagement |  | 3 | 30 | 27
Total Project Duration (In Months from NTP): |  |  |  |  | 30

## SSB - with ICR (hidden)
Scope, Schedule, and Budget Worksheet
Grant Program: | [10 empty] | Smart Growth Incentive Program - Capital Project
Will the matching funds include TransNet Local Streets and Road (LSI)? | [10 empty] | Smart Growth Incentive Program - Planning Project
Jurisdiction: | [10 empty] | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital Project
Part I: Project Overview | [10 empty] | Smart Growth Incentive Program - Complete Streets Policy
Project Title: |  | [Copy and paste from application] | [8 empty] | Smart Grwoth Incentive Program - Climate Action Plan
Project Limit: |  | [Copy and paste from application]
Yes
Project Summary: |  | [Copy and paste from application] | [8 empty] | No
Part II: Scope of Work, Schedule, and Budget
Propose tasks, deliverables, a timeframe, and a budget for implementing the project. The project schedule must be based on "Months from Notice to Proceed" (NTP) and should comply with Board Policy No. 035 timelines. The Total Project Cost column will auto-calculate. Capital projects are required to include $5,000 for baseline bike and pedestrian data collection. If this SSB is for a SGIP Planning, ATGP Non-Capital, SGIP - CAP, or SGIP - Complete Streets Policy project, overwrite line item 1 in the table below.
Task No. | Task Description |  |  | Deliverables |  | Start Date | Completion Date | Total Project Cost |  | Indirect Cost
Enter Task or Subtask Number (tailor as needed) | Enter task descriptions. Please limit tasks to 3 - 6 main tasks. Limit sub-tasks to major milestones. |  |  | Enter deliverables associated with each task. |  | Enter start date as number of months from NTP. Enter whole numbers only. | Enter end date as number of months from NTP. Enter whole numbers only. | Enter cost to complete each task. Sub-tasks should not have an associated cost. The total cost of all tasks should equal the total project cost (grant funds requested + matching funds). |  | If applicable, enter the approved indirect cost rate percentage in the box below
15%
1 | Collect Baseline Data (required for Capital projects only; remove this task if it is a planning project) |  |  | Baseline Data Collection Plan; Raw Bike/Ped Data |  |  |  | 5000 |  | 5750
2 | [7 empty] | 0 |  | 0
2a | [7 empty] | 0 |  | 0
2b | [7 empty] | 0 |  | 0
3 | [7 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
TOTAL PROJECT COST (grant request funds + matching funds): | [8 empty] | 5000 | 5750
Seasonal Constraints
As applicable, identify any seasonal constraints that may require the overall project, or specific tasks, to begin or be completed by a specific date:
Part III: Summary of Funding
| Total project cost: |  |  |  |  | 5000
| Total grant amount requested from SANDAG: |  |  |  |  | [Insert grant amount requested]
| Total match amount that will be contributed: |  |  |  |  | [Insert match contribution]
| SANDAG grant % contribution: |  |  |  |  | #VALUE!
| Match % contribution: |  |  |  |  | #VALUE!
Will the matching funds include TransNet Local Streets and Road (LSI)?
Part IV: Project Budget Expenditures per Year
SANDAG staff will reference this information for RTIP programming if this project receives funding.
Category* |  | Fiscal Year (FY) 2019 (July 1, 2018 - June 30, 2019) |  | FY 2020 (if applicable) (July 1, 2019 - June 30, 2020) |  | FY 2021 (if applicable) (July 1, 2020 - June 30, 2021) |  | FY 2022 (if applicable) (July 1, 2021 - June 30, 2022)
|  | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
ENV/ENGR
ROW
CONSTRUCTION
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Category* |  | FY 2023 (if applicable) (July 1, 2022 - June 30, 2023) |  | Total Grant Amount | Total Matching Funds | Total Project Cost |  | *Key
|  | Grant Amount | Match Amount |  |  |  |  | Category | Category Description
ENV/ENGR |  |  |  | 0 | 0 | 0 |  | ENV/ENGR | Environmental, Engineering, and Planning
ROW |  |  |  | 0 | 0 | 0
CONSTRUCTION |  |  |  | 0 | 0 | 0 |  | ROW | Right-of-Way
Total |  | 0 | 0 | 0 | 0 | 0 |  | CONSTRUCTION | Construction