## Project Scope and Budget
Scope of Work and Budget
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of Solana Beach
Project Type: |  | Climate Action Plan |  | [Select from the options in the dropdown field. Note: for Capital Projects, use the Capital Project Template.]
Project Title: |  | Regional Greenhouse Gas Emission Inventory Project
Part I: Project Overview
Project Location: |  | Jurisdictional limits of: City of Solana Beach, City of Carlsbad, City of Chula Vista, City of Encinitas, City of Escondido, City of La Mesa, City of Oceanside, and unincorporated County of San Diego.
Brief Project Summary: |  | Jurisdictions within San Diego County, including unincorporated County of San Diego, who have either updated their Climate Action Plan within the past year or anticipate completing their Climate Action Plan Update within the year, are proposing a joint project to complete multiple community-wide greenhouse gas emission (GHG) inventories. Through a multi-jurisdictional approach, economies of scale will be leveraged. The updated GHG inventories will allow the jurisdictions to meet monitoring requirements in their Climate Action Plans, refine and reprioritize emission reduction measures and increase transparency within their communities.
Project Objectives: |  | All participating jurisdictions have either adopted a CAP Update in the past year or anticipate the adoption of a CAP Update before the end of 2026. Each of these CAPs have a baseline GHG emission inventory, ranging from 2012 - 2019. This project would develop two nonconsecutive year community-wide GHG inventories and associated reports for each participating jurisdiction using the best available data. Regular GHG emissions inventories are outlined in each jurisdiction’s CAP (e.g., implementation chapter, formal Implementation Plan). The updated GHG inventories will then be used to prepare current monitoring reports for each jurisdiction to better inform current CAP implementation and allow for data-informed decision making when prioritizing and carrying out CAP projects, programs, and outreach efforts.
Part II: Scope of Work and Budget
[List the main project tasks in the grey-shaded spaces below. Include the task description, task outcome/output, deliverables, and grant and matching funds amount. Under each project task, include the subtasks that will be necessary to complete the main project task and include the subtask outcome/output, deliverables, and grant and matching funds. Add rows as needed. The Total Project Cost column will auto-calculate and is the sum of the SGIP grant and the matching funds.]
Task No. | Task Description |  |  | Task Outcome/Output |  | Deliverables |  | SGIP Grant Amount | Matching Funds Amount | Total Project Cost
1 | Hire a Consultant |  |  | The desired outcome of this task is to create and publish a Request for Proposals (RFP), review proposals, and execute a contract with the selected Consultant. |  | Release an RFP, select a Consultant, execute a contract with the Consultant |  | 0 | 6402.4 | 6402.4
1A | Create and publish a Request for Proposals. |  |  | RFP Published |  | RFP |  | 0 | 2134.1333 | 2134.1333
1B | City of Solana Beach and participating jurisdictions review proposals and select a Consultant. |  |  | Proposals reviewed and Consultant selected |  | Consultant selected |  | 0 | 2134.1333 | 2134.1333
1C | City of Solana Beach will work with the selected Consultant and execute a contract. |  |  | Contract with Consultant executed |  | Executed contract |  | 0 | 2134.1333 | 2134.1333
2 | Project Administration |  |  | The desired outcome of this task is to conduct project administration. |  | Kick-off meeting materials (x1) Project check-in meeting materials (x24) Data collection meeting materials (x8) |  | 20000 | 56021 | 76021
2A | Kick-off meeting |  |  | The desired outcome of this subtask is to hold a project kick-off meeting |  | Meeting materials (x1) |  | 1000 | 400.15 | 1400.15
2B | Regular project check-ins |  |  | The desired outcome of this subtask is to hold regular project check-ins. These check-ins will be monthly, at a minimum |  | Meeting materials (x24) |  | 16000 | 54580.46 | 16000
2C | Meetings with relevant agency staff and departments to collect data |  |  | The desired outcome of this subtask is to hold meetings with relevant agency staff, as appropriate, to collect inventory data. It is estimated that one meeting would be needed for each agency. |  | Meeting materials (x8) |  | 3000 | 1040.39 | 4040.39
3 | Update Communitywide GHG Inventories |  |  | The desired outcome of this task will be to update the communitywide GHG inventories for each agency using the best available data. It is expected that 2 communitywide GHG inventories will be prepared for each agency during the grant time period. |  | Summary of data needed per agency (x16) Summary of new potential data sources (x2) Communitywide GHG emissions inventory data per agency (x16) |  | 150000 | 0 | 150000
3A | Identify data needs |  |  | The desired outcome of this subtask is to identify the data needed for each agency to estimated communitywide GHG emissions. |  | Summary of data needed per agency (x16) |  | 30000 | 0 | 30000
3B | Review new potential data sources for any sectors with unidentified data needs |  |  | The desired outcome of this subtask is to explore new, alternative data sources, as needed, to complete the inventories in a timely manner |  | Summary of new potential data sources (x2) |  | 10000 | 0 | 10000
3C | Collect data |  |  | The desired outcome for this subtask is to collect all necessary data for the communitywide GHG inventory estimates |  | Data collection templates (x2) |  | 10000 | 0 | 10000
3D | Develop inventories |  |  | The desired outcome for this subtask is to estimate the communitywide GHG emissions for each agency using existing methods and best practices |  | Communitywide GHG emissions inventory data per agency (x16) |  | 100000 | 0 | 100000
4 | Summarize Methods and Findings |  |  | The desired outcome for this task is to develop technical reports to summarize the findings of and methods used to estimate communitywide GHG emissions per agency. It is estimated that one technical report will accompany each GHG inventory for a total of 16 technical reports. |  | Draft technical reports per agency (x16) Draft summary of results spreadsheet (x16) Meeting materials (x16) Final technical reports per agency (x16) Final summary of results spreadsheet (x16) |  | 150000 | 0 | 150000
4A | Develop draft technical report |  |  | The desired outcome for this subtask is to develop draft technical reports per inventory per agency. A spreadsheet summarizing the inventory results will also be developed. |  | Draft technical reports per agency (x16) Draft summary of results spreadsheet (x16) |  | 95000 | 0 | 95000
4B | Meetings to discuss draft technical report |  |  | The desired outcome for this subtask is to meet with each agency to discuss the draft technical reports and GHG inventories. This will help to answer questions and streamline edits to complete the final technical reports |  | Meeting materials (x16) |  | 5000 | 0 | 5000
4C | Finalize technical report |  |  | The desired outcome for this subtask is to finalize the technical reports per inventory per agency. The spreadsheet summarizing the inventory results will also be finalized. |  | Final technical reports per agency (x16) Final summary of results spreadsheet (x16) |  | 50000 | 0 | 50000
5 | Progress Reporting |  |  | The purpose of this task is to receive regular progress reports on the project. |  | Progress reports (x24) |  | 10000 | 0 | 10000
5A | Progress reporting |  |  | The purpose of this subtask is to receive regular progress reports on work completed, work remaining, and any challenges or issues. These can be presented at the regular project check-ins |  | Progress reports (x24) |  | 10000 | 0 | 10000
6 | Share Results |  |  | The purpose of this task is to share the results of the updated GHG inventories with the public and interested stakeholders of each agency |  | Monitoring reports x16 Presentation materials (x16) Public meeting materials (x16) |  | 70000 | 0 | 70000
6A | Prepare monitoring reports |  |  | The purpose of this subtask is to prepare monitoring report content on the updated GHG inventories. A minimum of 1 monitoring report per agency per inventory is exepcted. |  | Monitoring reports x16 |  | 30000 | 0 | 30000
6B | Prepare presentation materials and other collateral |  |  | The purpose of this subtask is to prepare presentation materials and other collateral (e.g., flyers), as appropriate, with information on the updated GHG inventories. |  | Presentation materials (x16) |  | 30000 | 0 | 30000
6C | Public meeting presentations |  |  | The purpose of this subtask is to share the results of the updated GHG inventories at agency public meetings (e.g., Board of Supervisors, City Council). A minimum of 1 public meeting per agency per inventory is expected. |  | Public meeting materials (x16) |  | 10000 | 0 | 10000
TOTAL PROJECT COST: | [7 empty] | 400000 | 62423.4 | 462423.4
Part III: Summary of Funding
[This information will be populated using information from Part II. Make a selection in the unshaded cell only.]
Total Project Cost: |  | 462423.4
Total Grant Request: |  | 400000
Total Matching Funds: |  | 62423.4
Grant Percentage: |  |  | 86.5%
Matching Funds Percentage: |  |  | 13.5%
Will any of the matching funds be from the TransNet Local Street and Road program? |  |  | No
Part IV: Project Budget and Expenditures Per Fiscal Year
[SANDAG staff will use this information for the Regional Transportation Improvement Program (RTIP) if this project receives funding. Fill in the unshaded cells only.]
Category* | Fiscal Year (FY) 2026 (NTP - June 30, 2026) |  | Fiscal Year (FY) 2027 (July 1, 2026 - June 30, 2027) |  | Fiscal Year (FY) 2028 (July 1, 2027 - June 30, 2028) |  | Fiscal Year (FY) 2029 (July 1, 2028 - June 30, 2029) |  | Total Grant Amount | Total Matching Funds | Total Project Cost
| Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
PE | 66668 | 17206.45 | 158332 | 20807.8 | 158332 | 20807.8 | 16668 | 3601.35 | 400000 | 62423.4 | 462423.4
RW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 66668 | 17206.45 | 158332 | 20807.8 | 158332 | 20807.8 | 16668 | 3601.35 | 400000 | 62423.4 | 462423.4
83874.45
*Key
Category | Category Description
PE | Planning, Environmental, and Engineering
RW | Right-of-Way
CON | Construction

## Project Schedule
Project Schedule
Instructions: Complete this form using the instructions provided in green italicized text.
Applicant Name: |  | City of Solana Beach |  |  |  | Smart Growth Incentive Program - Climate Action Plan
Smart Growth Incentive Program - Complete Streets Policy
Project Type: |  | Climate Action Plan | [Select from the options in the dropdown field. Note: for Capital Projects, use the Capital Project Template.]
Project Title: |  | Regional Greenhouse Gas Emission Inventory Project |  |  |  | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital
Part II: Project Schedule
[Propose a timeframe for each Project task and subtask. The schedule must use the same tasks and subtasks that are in the Scope of Work and be based on the number of months from the Notice to Proceed (NTP).]
Task No. | Task Description |  | Start Date | Completion Date | Duration
1 | Hire a Consultant |  | 1 | 4 | 3
1A | Create and publish RFP |  | 1 | 1 | 1
1B | Select Consultant |  | 2 | 2 | 1
1C | Execute contract with Consultant |  | 3 | 4 | 2
2 | Project Administration |  | 1 | 36 | 34
2A | Kick-off meeting |  | 4 | 4 | 1
2B | Regular project check-ins |  | 5 | 36 | 31
2C | Meetings with relevant agency staff and departments to collect data |  | 5 | 18 | 13
3 | Update Communitywide GHG Inventories |  | 4 | 18 | 14
3A | Identify data needs |  | 4 | 6 | 2
3B | Review new potential data sources for any sectors with unidentified data needs |  | 6 | 8 | 2
3C | Collect data |  | 8 | 12 | 4
3D | Develop inventories |  | 12 | 18 | 6
4 | Summarize Methods and Findings |  | 13 | 20 | 7
4A | Develop draft technical report |  | 13 | 16 | 3
4B | Meet to discuss draft technical report |  | 16 | 18 | 2
4C | Finalize technical report |  | 18 | 20 | 2
5 | Progress Reporting |  | 2 | 36 | 34
5A | Progress reporting |  | 2 | 36 | 34
6 | Share Results |  | 17 | 36 | 19
6A | Prepare monitoring reports |  | 17 | 23 | 6
6B | Prepare presentation materials and other collateral |  | 18 | 24 | 6
6C | Public meeting presentations |  | 24 | 36 | 12
Total Project Duration (In Months from NTP): |  |  |  |  | 36

## SSB - with ICR (hidden)
Scope, Schedule, and Budget Worksheet
Grant Program: | [10 empty] | Smart Growth Incentive Program - Capital Project
Will the matching funds include TransNet Local Streets and Road (LSI)? | [10 empty] | Smart Growth Incentive Program - Planning Project
Jurisdiction: | [10 empty] | Active Transportation Grant Program - Capital Project
Active Transportation Grant Program - Non-Capital Project
Part I: Project Overview | [10 empty] | Smart Growth Incentive Program - Complete Streets Policy
Project Title: |  | [Copy and paste from application] | [8 empty] | Smart Grwoth Incentive Program - Climate Action Plan
Project Limit: |  | [Copy and paste from application]
Yes
Project Summary: |  | [Copy and paste from application] | [8 empty] | No
Part II: Scope of Work, Schedule, and Budget
Propose tasks, deliverables, a timeframe, and a budget for implementing the project. The project schedule must be based on "Months from Notice to Proceed" (NTP) and should comply with Board Policy No. 035 timelines. The Total Project Cost column will auto-calculate. Capital projects are required to include $5,000 for baseline bike and pedestrian data collection. If this SSB is for a SGIP Planning, ATGP Non-Capital, SGIP - CAP, or SGIP - Complete Streets Policy project, overwrite line item 1 in the table below.
Task No. | Task Description |  |  | Deliverables |  | Start Date | Completion Date | Total Project Cost |  | Indirect Cost
Enter Task or Subtask Number (tailor as needed) | Enter task descriptions. Please limit tasks to 3 - 6 main tasks. Limit sub-tasks to major milestones. |  |  | Enter deliverables associated with each task. |  | Enter start date as number of months from NTP. Enter whole numbers only. | Enter end date as number of months from NTP. Enter whole numbers only. | Enter cost to complete each task. Sub-tasks should not have an associated cost. The total cost of all tasks should equal the total project cost (grant funds requested + matching funds). |  | If applicable, enter the approved indirect cost rate percentage in the box below
15%
1 | Collect Baseline Data (required for Capital projects only; remove this task if it is a planning project) |  |  | Baseline Data Collection Plan; Raw Bike/Ped Data |  |  |  | 5000 |  | 5750
2 | [7 empty] | 0 |  | 0
2a | [7 empty] | 0 |  | 0
2b | [7 empty] | 0 |  | 0
3 | [7 empty] | 0 |  | 0
[8 empty] | 0 |  | 0
TOTAL PROJECT COST (grant request funds + matching funds): | [8 empty] | 5000 | 5750
Seasonal Constraints
As applicable, identify any seasonal constraints that may require the overall project, or specific tasks, to begin or be completed by a specific date:
Part III: Summary of Funding
| Total project cost: |  |  |  |  | 5000
| Total grant amount requested from SANDAG: |  |  |  |  | [Insert grant amount requested]
| Total match amount that will be contributed: |  |  |  |  | [Insert match contribution]
| SANDAG grant % contribution: |  |  |  |  | #VALUE!
| Match % contribution: |  |  |  |  | #VALUE!
Will the matching funds include TransNet Local Streets and Road (LSI)?
Part IV: Project Budget Expenditures per Year
SANDAG staff will reference this information for RTIP programming if this project receives funding.
Category* |  | Fiscal Year (FY) 2019 (July 1, 2018 - June 30, 2019) |  | FY 2020 (if applicable) (July 1, 2019 - June 30, 2020) |  | FY 2021 (if applicable) (July 1, 2020 - June 30, 2021) |  | FY 2022 (if applicable) (July 1, 2021 - June 30, 2022)
|  | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount | Grant Amount | Match Amount
ENV/ENGR
ROW
CONSTRUCTION
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Category* |  | FY 2023 (if applicable) (July 1, 2022 - June 30, 2023) |  | Total Grant Amount | Total Matching Funds | Total Project Cost |  | *Key
|  | Grant Amount | Match Amount |  |  |  |  | Category | Category Description
ENV/ENGR |  |  |  | 0 | 0 | 0 |  | ENV/ENGR | Environmental, Engineering, and Planning
ROW |  |  |  | 0 | 0 | 0
CONSTRUCTION |  |  |  | 0 | 0 | 0 |  | ROW | Right-of-Way
Total |  | 0 | 0 | 0 | 0 | 0 |  | CONSTRUCTION | Construction